## Element List
ID | Description | Status | Planned Completion Date
122477 | M_Concrete-Round-Column |  | 2016-08-31 17:00
122478 | M_Concrete-Round-Column |  | 2016-08-31 17:00
122479 | M_Concrete-Round-Column |  | 2016-08-31 17:00
122480 | M_Concrete-Round-Column | In Progress | 2016-08-25 17:00
122481 | M_Concrete-Round-Column | In Progress | 2016-08-25 17:00
122482 | M_Concrete-Round-Column | In Progress | 2016-08-25 17:00
122483 | M_Concrete-Round-Column | In Progress | 2016-08-25 17:00
122484 | M_Concrete-Round-Column | Completed | 2016-08-15 08:00
122485 | M_Concrete-Round-Column | Completed | 2016-08-15 08:00
122486 | M_Concrete-Round-Column | Completed | 2016-08-15 08:00
122487 | M_Concrete-Round-Column | In Progress | 2016-08-25 17:00
122488 | M_Concrete-Round-Column | In Progress | 2016-08-25 17:00
122490 | M_Concrete-Round-Column |  | 2016-08-31 17:00
122491 | M_Concrete-Round-Column |  | 2016-08-31 17:00
122492 | M_Concrete-Round-Column |  | 2016-08-31 17:00
122493 | M_Concrete-Round-Column | In Progress | 2016-08-25 17:00
122494 | M_Concrete-Round-Column | In Progress | 2016-08-25 17:00
122495 | M_Concrete-Round-Column | In Progress | 2016-08-25 17:00
122496 | M_Concrete-Round-Column | In Progress | 2016-08-25 17:00
122497 | M_Concrete-Round-Column | Completed | 2016-08-15 08:00
122498 | M_Concrete-Round-Column | Completed | 2016-08-15 08:00
122500 | M_Concrete-Round-Column | In Progress | 2016-08-25 17:00
122501 | M_Concrete-Round-Column | In Progress | 2016-08-25 17:00
122503 | M_Concrete-Round-Column |  | 2016-08-31 17:00
122504 | M_Concrete-Round-Column |  | 2016-08-31 17:00
122505 | M_Concrete-Round-Column |  | 2016-08-31 17:00
122506 | M_Concrete-Round-Column | In Progress | 2016-08-25 17:00
122507 | M_Concrete-Round-Column | In Progress | 2016-08-25 17:00
122508 | M_Concrete-Round-Column | In Progress | 2016-08-25 17:00
122509 | M_Concrete-Round-Column | In Progress | 2016-08-25 17:00
122510 | M_Concrete-Round-Column | Completed | 2016-08-15 08:00
122511 | M_Concrete-Round-Column | Completed | 2016-08-15 08:00
122512 | M_Concrete-Round-Column | Completed | 2016-08-15 08:00
122513 | M_Concrete-Round-Column | In Progress | 2016-08-25 17:00
122514 | M_Concrete-Round-Column | In Progress | 2016-08-25 17:00
122516 | M_Concrete-Round-Column |  | 2016-08-31 17:00
122517 | M_Concrete-Round-Column |  | 2016-08-31 17:00
122520 | M_Concrete-Round-Column | Completed | 2016-08-15 08:00
122521 | M_Concrete-Round-Column | Completed | 2016-08-15 08:00
122524 | M_Concrete-Round-Column |  | 2016-08-31 17:00
122525 | M_Concrete-Round-Column |  | 2016-08-31 17:00
122528 | M_Concrete-Round-Column | Completed | 2016-08-15 08:00
122529 | M_Concrete-Round-Column | Completed | 2016-08-15 08:00
122536 | M_Concrete-Round-Column | Completed | 2016-08-15 08:00
122537 | M_Concrete-Round-Column | Completed | 2016-08-15 08:00
122541 | M_Concrete-Round-Column | Completed | 2016-08-15 08:00
122542 | M_Concrete-Round-Column | Completed | 2016-08-15 08:00
122544 | M_Concrete-Round-Column | Completed | 2016-08-15 08:00
122545 | M_Concrete-Round-Column | Completed | 2016-08-15 08:00
122547 | M_Concrete-Round-Column | Completed | 2016-08-15 08:00
122548 | M_Concrete-Round-Column | Completed | 2016-08-15 08:00
122552 | M_Concrete-Round-Column |  | 2016-08-31 17:00
122553 | M_Concrete-Round-Column |  | 2016-08-31 17:00
122556 | M_Concrete-Round-Column |  | 2016-08-31 17:00
122559 | M_Concrete-Round-Column | In Progress | 2016-08-25 17:00
122562 | M_Concrete-Round-Column | In Progress | 2016-08-25 17:00
122565 | M_Concrete-Round-Column | In Progress | 2016-08-25 17:00
122566 | M_Concrete-Round-Column | In Progress | 2016-08-25 17:00
122567 | M_Concrete-Round-Column | Completed | 2016-08-15 08:00
122568 | M_Concrete-Round-Column | Completed | 2016-08-15 08:00
122569 | M_Concrete-Round-Column | Completed | 2016-08-15 08:00
122570 | M_Concrete-Round-Column | In Progress | 2016-08-25 17:00
122571 | M_Concrete-Round-Column | In Progress | 2016-08-25 17:00
123276 | Basic Wall |  | 2016-08-31 17:00
123964 | Basic Wall |  | 2016-08-31 17:00
124071 | Basic Wall | Completed | 2016-08-15 08:00
124110 | Basic Wall | Completed | 2016-08-15 08:00
124559 | M_Concrete-Rectangular Beam |  | 2016-08-31 17:00
124565 | M_Concrete-Rectangular Beam |  | 2016-08-31 17:00
124568 | M_Concrete-Rectangular Beam | In Progress | 2016-08-25 17:00
124571 | M_Concrete-Rectangular Beam | In Progress | 2016-08-25 17:00
124574 | M_Concrete-Rectangular Beam | In Progress | 2016-08-25 17:00
124577 | M_Concrete-Rectangular Beam | In Progress | 2016-08-25 17:00
124579 | M_Concrete-Rectangular Beam | In Progress | 2016-08-25 17:00
124582 | M_Concrete-Rectangular Beam | In Progress | 2016-08-25 17:00
124585 | M_Concrete-Rectangular Beam | In Progress | 2016-08-25 17:00
124587 | M_Concrete-Rectangular Beam | Completed | 2016-08-15 08:00
124590 | M_Concrete-Rectangular Beam | Completed | 2016-08-15 08:00
124592 | M_Concrete-Rectangular Beam |  | 2016-08-31 17:00
124594 | M_Concrete-Rectangular Beam |  | 2016-08-31 17:00
124598 | M_Concrete-Rectangular Beam | In Progress | 2016-08-25 17:00
124600 | M_Concrete-Rectangular Beam | In Progress | 2016-08-25 17:00
124602 | M_Concrete-Rectangular Beam | In Progress | 2016-08-25 17:00
124604 | M_Concrete-Rectangular Beam | In Progress | 2016-08-25 17:00
124606 | M_Concrete-Rectangular Beam | In Progress | 2016-08-25 17:00
124608 | M_Concrete-Rectangular Beam | In Progress | 2016-08-25 17:00
124610 | M_Concrete-Rectangular Beam | In Progress | 2016-08-25 17:00
124612 | M_Concrete-Rectangular Beam | Completed | 2016-08-15 08:00
124614 | M_Concrete-Rectangular Beam |  | 2016-08-31 17:00
124616 | M_Concrete-Rectangular Beam |  | 2016-08-31 17:00
124620 | M_Concrete-Rectangular Beam | In Progress | 2016-08-25 17:00
124622 | M_Concrete-Rectangular Beam | In Progress | 2016-08-25 17:00
124624 | M_Concrete-Rectangular Beam | In Progress | 2016-08-25 17:00
124626 | M_Concrete-Rectangular Beam | In Progress | 2016-08-25 17:00
124628 | M_Concrete-Rectangular Beam | In Progress | 2016-08-25 17:00
124630 | M_Concrete-Rectangular Beam | In Progress | 2016-08-25 17:00
124632 | M_Concrete-Rectangular Beam | In Progress | 2016-08-25 17:00
124634 | M_Concrete-Rectangular Beam | Completed | 2016-08-15 08:00
124636 | M_Concrete-Rectangular Beam | Completed | 2016-08-15 08:00
124638 | M_Concrete-Rectangular Beam |  | 2016-08-31 17:00
124645 | M_Concrete-Rectangular Beam | Completed | 2016-08-15 08:00
124647 | M_Concrete-Rectangular Beam |  | 2016-08-31 17:00
124653 | M_Concrete-Rectangular Beam | Completed | 2016-08-15 08:00
124655 | M_Concrete-Rectangular Beam | Completed | 2016-08-15 08:00
124657 | M_Concrete-Rectangular Beam | Completed | 2016-08-15 08:00
124659 | M_Concrete-Rectangular Beam | Completed | 2016-08-15 08:00
124661 | M_Concrete-Rectangular Beam | Completed | 2016-08-15 08:00
124666 | M_Concrete-Rectangular Beam |  | 2016-08-31 17:00
124669 | M_Concrete-Rectangular Beam |  | 2016-08-31 17:00
124672 | M_Concrete-Rectangular Beam |  | 2016-08-31 17:00
124674 | M_Concrete-Rectangular Beam |  | 2016-08-31 17:00
124677 | M_Concrete-Rectangular Beam |  | 2016-08-31 17:00
124680 | M_Concrete-Rectangular Beam |  | 2016-08-31 17:00
124684 | M_Concrete-Rectangular Beam |  | 2016-08-31 17:00
124686 | M_Concrete-Rectangular Beam |  | 2016-08-31 17:00
124688 | M_Concrete-Rectangular Beam |  | 2016-08-31 17:00
124690 | M_Concrete-Rectangular Beam |  | 2016-08-31 17:00
124692 | M_Concrete-Rectangular Beam |  | 2016-08-31 17:00
124694 | M_Concrete-Rectangular Beam |  | 2016-08-31 17:00
124696 | M_Concrete-Rectangular Beam |  | 2016-08-31 17:00
124698 | M_Concrete-Rectangular Beam |  | 2016-08-31 17:00
124707 | M_Concrete-Rectangular Beam | In Progress | 2016-08-25 17:00
124709 | M_Concrete-Rectangular Beam | In Progress | 2016-08-25 17:00
124713 | M_Concrete-Rectangular Beam | In Progress | 2016-08-25 17:00
124715 | M_Concrete-Rectangular Beam | In Progress | 2016-08-25 17:00
124724 | M_Concrete-Rectangular Beam | In Progress | 2016-08-25 17:00
124726 | M_Concrete-Rectangular Beam | In Progress | 2016-08-25 17:00
124730 | M_Concrete-Rectangular Beam | In Progress | 2016-08-25 17:00
124732 | M_Concrete-Rectangular Beam | In Progress | 2016-08-25 17:00
124736 | M_Concrete-Rectangular Beam | Completed | 2016-08-15 08:00
124742 | M_Concrete-Rectangular Beam | Completed | 2016-08-15 08:00
124745 | M_Concrete-Rectangular Beam | Completed | 2016-08-15 08:00
124747 | M_Concrete-Rectangular Beam | Completed | 2016-08-15 08:00
124749 | M_Concrete-Rectangular Beam | Completed | 2016-08-15 08:00
124751 | M_Concrete-Rectangular Beam | Completed | 2016-08-15 08:00
124753 | M_Concrete-Rectangular Beam | Completed | 2016-08-15 08:00
124755 | M_Concrete-Rectangular Beam | Completed | 2016-08-15 08:00
124757 | M_Concrete-Rectangular Beam | Completed | 2016-08-15 08:00
124759 | M_Concrete-Rectangular Beam | Completed | 2016-08-15 08:00
124761 | M_Concrete-Rectangular Beam | Completed | 2016-08-15 08:00
124765 | M_Concrete-Rectangular Beam | Completed | 2016-08-15 08:00
124767 | M_Concrete-Rectangular Beam | Completed | 2016-08-15 08:00
124769 | M_Concrete-Rectangular Beam | Completed | 2016-08-15 08:00
124771 | M_Concrete-Rectangular Beam | Completed | 2016-08-15 08:00
124773 | M_Concrete-Rectangular Beam | Completed | 2016-08-15 08:00
124775 | M_Concrete-Rectangular Beam | Completed | 2016-08-15 08:00
124777 | M_Concrete-Rectangular Beam | Completed | 2016-08-15 08:00
124779 | M_Concrete-Rectangular Beam | Completed | 2016-08-15 08:00
124782 | M_Concrete-Rectangular Beam | Completed | 2016-08-15 08:00
124784 | M_Concrete-Rectangular Beam |  | 2016-08-31 17:00
124788 | M_Concrete-Rectangular Beam |  | 2016-08-31 17:00
124790 | M_Concrete-Rectangular Beam | In Progress | 2016-08-25 17:00
124792 | M_Concrete-Rectangular Beam | In Progress | 2016-08-25 17:00
124794 | M_Concrete-Rectangular Beam | In Progress | 2016-08-25 17:00
124796 | M_Concrete-Rectangular Beam | In Progress | 2016-08-25 17:00
124798 | M_Concrete-Rectangular Beam | In Progress | 2016-08-25 17:00
124800 | M_Concrete-Rectangular Beam | In Progress | 2016-08-25 17:00
124802 | M_Concrete-Rectangular Beam | In Progress | 2016-08-25 17:00
124804 | M_Concrete-Rectangular Beam | Completed | 2016-08-15 08:00
124806 | M_Concrete-Rectangular Beam | Completed | 2016-08-15 08:00
124808 | M_Concrete-Rectangular Beam | In Progress | 2016-08-25 17:00
124810 | M_Concrete-Rectangular Beam | In Progress | 2016-08-25 17:00
124812 | M_Concrete-Rectangular Beam | In Progress | 2016-08-25 17:00
124818 | M_Concrete-Rectangular Beam | In Progress | 2016-08-25 17:00
124820 | M_Concrete-Rectangular Beam | In Progress | 2016-08-25 17:00
124822 | M_Concrete-Rectangular Beam | In Progress | 2016-08-25 17:00
125944 | UB-Universal Beam
125958 | UB-Universal Beam
125972 | UB-Universal Beam
126003 | UB-Universal Beam
127308 | UB-Universal Beam
127484 | M_Concrete-Rectangular Beam | Completed | 2016-08-15 08:00
127485 | M_Concrete-Rectangular Beam | Completed | 2016-08-15 08:00
127486 | M_Concrete-Rectangular Beam | Completed | 2016-08-15 08:00
127516 | M_Concrete-Rectangular Beam | In Progress | 2016-08-25 17:00
127517 | M_Concrete-Rectangular Beam | In Progress | 2016-08-25 17:00
127518 | M_Concrete-Rectangular Beam | In Progress | 2016-08-25 17:00
127581 | M_Concrete-Rectangular Beam |  | 2016-08-31 17:00
127582 | M_Concrete-Rectangular Beam |  | 2016-08-31 17:00
127583 | M_Concrete-Rectangular Beam |  | 2016-08-31 17:00
127649 | M_Concrete-Rectangular Beam | In Progress | 2016-08-25 17:00
127650 | M_Concrete-Rectangular Beam | In Progress | 2016-08-25 17:00
127651 | M_Concrete-Rectangular Beam | In Progress | 2016-08-25 17:00
128135 | UB-Universal Beam
128137 | UB-Universal Beam
128139 | UB-Universal Beam
128141 | UB-Universal Beam
128143 | UB-Universal Beam
128145 | UB-Universal Beam
128147 | UB-Universal Beam
128213 | M_Concrete-Rectangular Beam |  | 2016-08-31 17:00
128264 | M_Concrete-Rectangular Beam |  | 2016-08-31 17:00
128318 | M_Concrete-Rectangular Beam | Completed | 2016-08-15 08:00
128344 | M_Concrete-Rectangular Beam | Completed | 2016-08-15 08:00
128372 | M_Concrete-Rectangular Beam | Completed | 2016-08-15 08:00
128397 | M_Concrete-Rectangular Beam | Completed | 2016-08-15 08:00
128432 | M_Concrete-Rectangular Beam | Completed | 2016-08-15 08:00
128473 | M_Concrete-Rectangular Beam | Completed | 2016-08-15 08:00
132740 | M_HSS-Round Structural Tubing
132741 | M_HSS-Round Structural Tubing
132742 | M_HSS-Round Structural Tubing
132744 | M_HSS-Round Structural Tubing
132745 | M_HSS-Round Structural Tubing
132746 | M_HSS-Round Structural Tubing
132748 | M_HSS-Round Structural Tubing
132749 | M_HSS-Round Structural Tubing
132750 | M_HSS-Round Structural Tubing
132751 | M_HSS-Round Structural Tubing
132752 | M_HSS-Round Structural Tubing
132753 | M_HSS-Round Structural Tubing
132754 | M_HSS-Round Structural Tubing
133227 | M_HSS-Round Structural Tubing
133228 | M_HSS-Round Structural Tubing
133229 | M_HSS-Round Structural Tubing
133230 | M_HSS-Round Structural Tubing
133231 | M_HSS-Round Structural Tubing
133232 | M_HSS-Round Structural Tubing
133233 | M_HSS-Round Structural Tubing
133234 | M_HSS-Round Structural Tubing
133235 | M_HSS-Round Structural Tubing
133236 | M_HSS-Round Structural Tubing
133237 | M_HSS-Round Structural Tubing
133238 | M_HSS-Round Structural Tubing
133239 | M_HSS-Round Structural Tubing
133345 | Floor |  | 2016-09-08 17:00
134840 | Floor
150648 | UB-Universal Beam
150724 | UB-Universal Beam